## Tracker
Page | Live URL | Page Type | Priority | AISEO (Title) | Meta Desc | Images Alt Text | Schema | Internal Linking | Owner / Assigned To | Target Date | Date Completed | % Complete | Notes / Team Comments | Recommended Page Title | Recommended Meta Description | Image Changed? - Review Alt | Billed - SEO | Billed - Schema | STILL TO BILL | Bill Date
Homepage | https://www.cleanroomfilm.com/ | Homepage | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-16 | 100% | IMPLEMENTED 2026-07-16 — H1 still split across three hero phrases ("From the tiniest of micro-chips" / "To life saving surgical tools" / …). Consolidate to one keyword-bearing H1, e.g. "Cleanroom Packaging Film & Bags — Sterile Delivery When It Matters Most", and demote narrative lines to styled paragraph text. | Cleanroom Packaging: Film & Bags Manufacturer ¦ CFB | ISO-certified cleanroom packaging manufacturer. Class 100 film & bags for medical, semiconductor, aerospace & pharma. USA made 35+ years. Get a quote. | Yes | Billed | Billed | -
Products (hub) | https://www.cleanroomfilm.com/products | Category | High | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Markets (hub) | https://www.cleanroomfilm.com/markets | Category | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-22 | 100% | IMPLEMENTED 2026-07-22 — Replaced the old title ("Markets ¦ Poly Bag & Blown Film Manufacturing ¦ Cleanroom Film & Bags") and a generic boilerplate meta that had appeared on the page since the original audit (which had found it missing entirely). Added CollectionPage schema listing all 7 market pages as hasPart, reinforcing | Industries We Serve: Medical, Semiconductor, Aerospace ¦ CFB | Cleanroom packaging for medical, pharmaceutical, semiconductor, aerospace, electronics & food industries. ISO-certified, USA-made film and bags. | Yes | Billed | Billed | -
Materials (hub) | https://www.cleanroomfilm.com/materials | Category | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-08-11 | 100% | IMPLEMENTED 2026-08-11 — Flagged by Ubersuggest as a too-long title (72 chars, confirmed live). Same pattern as the original /markets hub finding: title targets only ESD ("ESD Packaging Materials: Anti-Static Polyethylene Bags & Film ¦ LDPE") while the page covers 11 materials — a mismatch with its own H1 ("Cleanroom Packag | Cleanroom Packaging Materials: Nylon, Tyvek®, Aclar® & More ¦ CFB | Cleanroom packaging materials: Nylon, Tyvek®, Aclar®, CLEANTUFF®, ULO, ESD & more — 11 material options for medical, aerospace & semiconductor. | Yes | Billed | Billed | -
Standards | https://www.cleanroomfilm.com/standards | Info | High | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Our Story | https://www.cleanroomfilm.com/our-story | Info | Medium | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-22 | 100% | IMPLEMENTED 2026-07-22 — Replaced the original mismatched title/meta ("Sterile Packaging: Healthcare, Pharmaceutical, & Food Bags ¦ CFB") which had been live since the first audit. Added AboutPage schema with mainEntity pointing to the Organization. Added 3 internal links promoting the buried CLEANTUFF®/ULO exclusive-materi | Our Story: 35+ Years of Cleanroom Packaging Excellence ¦ CFB | 35+ years of cleanroom packaging excellence. Class 100 vertically integrated facility in Placentia, CA. Exclusive manufacturer of CLEANTUFF® and ULO films. | Yes | Billed | Billed | -
Contact Us | https://www.cleanroomfilm.com/contact-us | Info | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Learning Center (hub) | https://www.cleanroomfilm.com/learning-center | Blog Hub | Medium | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-08-11 | 100% | IMPLEMENTED 2026-08-11 — Found the weakest SEO on the entire site: page title was the bare company name ("Cleanroom Film & Bags", no keyword targeting) and meta description was the two-word placeholder "Learning Center" — likely never replaced since blog setup. Fixed both, plus the on-page Blog header field (visible H1-equi | Learning Center: Cleanroom Packaging Case Studies & News ¦ CFB | Explore CFB's cleanroom packaging case studies, product announcements, and industry insights — covering aerospace, semiconductor, and medical applications. | Yes | Billed | Billed | -
Medical Cleanroom Packaging | https://www.cleanroomfilm.com/markets/medical-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-16 | 100% | IMPLEMENTED 2026-07-16 — Current title is 76 chars (truncates); current meta has a live grammar error ("manufacturer of cleanroom bags and sterile for the medical cleanroom packaging market") — replace, don’t patch. H1 ("Medical Cleanroom Packaging Supplies") is fine. ~550–600 words, best content depth of the market pages. | Medical Cleanroom Packaging: CLEANTUFF® & LDPE Bags ¦ CFB | Medical cleanroom packaging in ISO-certified Class 100 cleanrooms — CLEANTUFF® LDPE film, nylon & sterile bags for medical devices. Get a quote. | Yes | Billed | Billed | -
Semiconductor Cleanroom Packaging | https://www.cleanroomfilm.com/markets/semiconductor-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-16 | 100% | IMPLEMENTED 2026-07-16 — Thinnest of the three market pages (~350–400 words) — expand toward 800 with wafer/FOUP applications and cleanliness specs. Add contextual links to the FOUP case study (exists in Learning Center) and the ULO material page — this page should be the hub for CFB’s strongest exclusive. Current title/met | Semiconductor Cleanroom Packaging: ULO Film & ESD Bags ¦ CFB | Semiconductor cleanroom packaging with extreme low outgassing (ULO) film and anti-static nylon — USA-made to ISO 14644 standards. Request a quote. | Yes | Billed | Billed | -
Aerospace Cleanroom Packaging | https://www.cleanroomfilm.com/markets/aerospace-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Strongest of the three pages — current meta is genuinely good (kept as-is above); current title fine but the recommended version adds the two differentiators buyers search. Alt text here is already partial-quality; the suggestions below are polish, not rescue. The space case study ("Strong Enough fo | Aerospace Cleanroom Packaging: ESD & Flame-Retardant ¦ CFB | CFB offers aerospace packaging including barrier packaging, ESD packaging, large part transit covers, cleanroom solutions, and flame retardant options. | Yes | Billed | Billed | -
Pharmaceutical Cleanroom Packaging | https://www.cleanroomfilm.com/markets/pharmaceutical-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Current meta is decent (sterilization-focused). ~350–400 words. H1 "Cleanroom Pharmaceutical Packaging" is fine but word order differs from URL/title — keep title keyword-first. Page claims FDA & EU compliance but the body does not name specific sterilization methods the meta references (gamma/heat/ | Pharmaceutical Cleanroom Packaging: FDA-Compliant Bags ¦ CFB | Pharmaceutical cleanroom packaging that ensures drug safety — ISO-certified LDPE, HDPE & nylon bags for gamma, heat & steam sterilization. Get a quote. | Yes | Billed | Billed | -
Healthcare Cleanroom Packaging | https://www.cleanroomfilm.com/markets/healthcare-cleanroom-packaging | Market | High | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Electronic Cleanroom Packaging | https://www.cleanroomfilm.com/markets/electronic-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Current meta is weak and shares the medical page’s boilerplate ("manufacturer of cleanroom bags and sterile packaging"). Best keyword-rich market page after aerospace — 6 H2s, ~450 words. IMPORTANT: CleanTronics™ is a CFB-branded electronics line (like CLEANTUFF®/ULO) — treat it as an exclusive keyw | Electronic Cleanroom Packaging: ESD & Anti-Static Bags ¦ CFB | Electronic cleanroom packaging for microelectronics — ESD, anti-static & static-shielding bags plus CFB CleanTronics™ advanced packaging. Get a quote. | Yes | Billed | Billed | -
Food Cleanroom Packaging | https://www.cleanroomfilm.com/markets/food-cleanroom-packaging | Market | High | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Thinnest market page (~320 words) and ranks #19 for "clean room for food packaging" (Search Volume 10) — low competition, easy win with more depth. Expand toward 600 words: add nylon barrier specs, custom sizing (12x18" to 26x34"), and food-safety certifications. Only 2 content images — consider add | Food Cleanroom Packaging: Nylon & High-Heat Oven Bags ¦ CFB | Food-grade cleanroom packaging — nylon bags and high-heat oven bags (to 375°F), BPA-free & FDA-approved for oven, microwave & freezer. Get a quote. | Yes | Billed | Billed | -
Aclar Cleanroom Packaging | https://www.cleanroomfilm.com/materials/aclar-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Anti-Static Nylon Cleanroom Packaging | https://www.cleanroomfilm.com/materials/anti-static-nylon-cleanroom-packaging | Material | Medium | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-08-11 | 100% | IMPLEMENTED 2026-08-11 — PRIORITY 1 from the July 28 progress report: "anti-static bags" is the single largest untapped keyword found in rank tracking — 4,400 searches/month, not yet ranking. Page is already substantial (~1,200–1,400 words, real CFB5100 spec table: tensile strength, surface resistivity, cleanliness level) — | Anti-Static Bags: Nylon Cleanroom Packaging ¦ CFB | Anti-static bags in cleanroom-grade nylon — ESD protection, color-coded identification, and durability for electronics, pharma & aerospace. Get a quote. | Yes | Billed | Billed | -
Barrier Cleanroom Packaging | https://www.cleanroomfilm.com/materials/barrier-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
CLEANTUFF Cleanroom Packaging | https://www.cleanroomfilm.com/materials/cleantuff-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
ESD Cleanroom Packaging | https://www.cleanroomfilm.com/materials/esd-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Extreme Low Outgassing (ULO) Cleanroom Packaging | https://www.cleanroomfilm.com/materials/extreme-low-outgassing-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Nylon/Polyethylene Cleanroom Packaging | https://www.cleanroomfilm.com/materials/nylon-polyethylene-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Polyethylene Cleanroom Packaging | https://www.cleanroomfilm.com/materials/polyethylene-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Static Shielding Cleanroom Packaging | https://www.cleanroomfilm.com/materials/static-shielding-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Tyvek Cleanroom Packaging | https://www.cleanroomfilm.com/materials/tyvek-cleanroom-packaging | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Nylon | https://www.cleanroomfilm.com/materials/nylon | Material | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Bags (hub) | https://www.cleanroomfilm.com/products/cleanroom-bags | Category | High | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Bags on a Roll | https://www.cleanroomfilm.com/products/cleanroom-bags/bags-on-a-roll | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Bottom Seal Bags | https://www.cleanroomfilm.com/products/cleanroom-bags/bottom-seal-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Header Bags | https://www.cleanroomfilm.com/products/cleanroom-bags/cleanroom-header-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Zipper Bags | https://www.cleanroomfilm.com/products/cleanroom-bags/cleanroom-zipper-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Gusseted Bags | https://www.cleanroomfilm.com/products/cleanroom-bags/gusseted-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
High Heat Oven Bags | https://www.cleanroomfilm.com/products/cleanroom-bags/high-heat-oven-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Tyvek Heat Sealing Pouches | https://www.cleanroomfilm.com/products/cleanroom-bags/tyvek-heat-sealing-pouches | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Film (hub) | https://www.cleanroomfilm.com/products/cleanroom-film | Category | High | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Rollstock | https://www.cleanroomfilm.com/products/cleanroom-film/cleanroom-rollstock | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Sheeting | https://www.cleanroomfilm.com/products/cleanroom-film/cleanroom-sheeting | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Square Bottom Covers | https://www.cleanroomfilm.com/products/cleanroom-film/cleanroom-square-bottom-covers | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Cleanroom Tubing | https://www.cleanroomfilm.com/products/cleanroom-film/cleanroom-tubing | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Aluminum Foil Bags | https://www.cleanroomfilm.com/products/aluminum-foil-bags | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Medical Film Rolls | https://www.cleanroomfilm.com/products/medical-film-rolls | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Medical Grade Paper Rolls | https://www.cleanroomfilm.com/products/medical-grade-paper-rolls | Product | Medium | Not Started | Not Started | Not Started | Not Started | Not Started |  |  |  | 0%
Case Study: FOUP Packaging (High-Density Resin) | https://www.cleanroomfilm.com/learning-center/case-study-cleanroom-film-bags-foup-packaging-using-high-density-resin | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 | Case Study: FOUP Packaging Using High-Density Resin ¦ CFB | Keep meta. Add Article schema. Cross-link to /markets/semiconductor (the semiconductor page audit already calls for this link). | Yes | Billed | Billed | -
Case Study: Aclar® Film at Boeing | https://www.cleanroomfilm.com/learning-center/case-study-the-use-of-aclar-packaging-film-for-protecting-parts-at-boeing | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Flagship E-E-A-T asset (names Boeing). Keep meta. Add Article schema. Cross-link to /materials/aclar and /markets/aerospace — currently orphaned from both. | Case Study: Aclar® Film Protecting Parts at Boeing ¦ CFB | Aclar® film case study: Boeing improves protection, reduces corrosion, and boosts efficiency with advanced moisture barrier packaging. | Yes | Billed | Billed | -
CFB Packaging Ensures Safe Organ Transplant | https://www.cleanroomfilm.com/learning-center/cfb-packaging-ensures-safe-organ-transplant | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 | CFB Packaging Ensures Safe Organ Transplant ¦ CFB | Powerful E-E-A-T story. Keep meta. Add Article schema. Link to /markets/medical and /markets/healthcare. | Yes | Billed | Billed | -
CFB Packaging Strong Enough for Outer Space | https://www.cleanroomfilm.com/learning-center/cfb-packaging-strong-enough-for-outer-space | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 | CFB Packaging Strong Enough for Outer Space ¦ CFB | Keep meta. Add Article schema. Already featured on /markets/aerospace — ensure the reverse link exists too. The -455°F / CFB7000 HydroBlock® detail is a standout hook. | Yes | Billed | Billed | -
Adds Capacity for Nylon Films & Bags | https://www.cleanroomfilm.com/learning-center/cleanroom-film-bags-adds-capacity-to-serve-increasing-demand-for-cleanroom-nylon-films-and-bags | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Keep meta. Trim title from full headline. Add NewsArticle schema. Link to /materials/nylon. | Adds Cleanroom Nylon Film & Bag Capacity ¦ CFB | CFB expands nylon cleanroom packaging capacity, delivering high-purity, durable films with fast lead times for medical, aerospace, and tech. | Yes | Billed | Billed | -
Adds High-Speed Converting Line | https://www.cleanroomfilm.com/learning-center/cleanroom-film-bags-adds-high-speed-converting-line-to-serve-increasing-demand-for-cleanroom-bags | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Current meta is good — keep. Current title is the full editorial headline (~92 chars, truncates); trimmed version keeps news value under 60. Add NewsArticle schema + author byline. Internal-link to /products/cleanroom-bags. | Adds High-Speed Converting Line for Cleanroom Bags ¦ CFB | CFB adds high-speed converting line to boost cleanroom bag production, delivering faster lead times, strong seals, and reliable performance. | Yes | Billed | Billed | -
Announces CFB CleanTronics™ | https://www.cleanroomfilm.com/learning-center/cfb-cleantronics-launch | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — ORIGINAL published date confirmed as 2024-03-26 (visible on live page) — use that in schema, NOT the Apr 2026 migration date. Announces the CleanTronics™ brand — link to /markets/electronic where the brand is featured. Keep meta. URL SHORTENED 2026-08-11 per Ubersuggest flag: was /learning-center/cl | CFB Announces CleanTronics™ Advanced Packaging ¦ CFB | CFB launches CleanTronics advanced packaging for semiconductors, offering low outgassing, ESD protection, and ultra-clean solutions. | Yes | Billed | Billed | -
Expands Sterilizable Packaging | https://www.cleanroomfilm.com/learning-center/cleanroom-film-bags-expands-offering-of-customized-sterilizable-packaging | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 — Keep meta. Add NewsArticle schema. Link to /materials/tyvek and /markets/medical. | Expands Customized Sterilizable Tyvek® Packaging ¦ CFB | CFB expands Tyvek® sterilizable packaging, offering durable, customizable solutions for medical devices with superior barrier protection. | Yes | Billed | Billed | -
Opens State-of-the-Art Plant in Placentia | https://www.cleanroomfilm.com/learning-center/cleanroom-film-bags-opens-state-of-the-art-plant-in-placentia | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 | CFB Opens State-of-the-Art Plant in Placentia ¦ CFB | Keep meta. Add NewsArticle schema. Local-SEO value (names Placentia) — link to /contact-us and /our-story; supports the LocalBusiness entity. | Yes | Billed | Billed | -
How To Choose the Right Medical Device Packaging | https://www.cleanroomfilm.com/learning-center/how-to-choose-the-right-medical-device-packaging | Blog | Low | Complete | Complete | Complete | Complete | Complete | Start Advertising |  | 2026-07-17 | 100% | IMPLEMENTED 2026-07-17 | How To Choose the Right Medical Device Packaging ¦ CFB | Only informational/guide article in the set — highest evergreen SEO value (targets a real informational query). Keep meta. Consider HowTo or FAQ schema in addition to Article. Link to /markets/medical and /standards. Strong candidate for expansion into a pillar guide. | Yes | Billed | Billed | -

## Summary
Cleanroom Film & Bags — SEO Project Tracker
Prepared by Start Advertising
Total pages (sitemap) | 52
Pages audited | 22
Pages implemented | 22
Pages remaining | 30
% complete (implemented)
Legend
Green rows | Implemented in HubSpot
Amber rows | Audited — pending implementation
Untinted | Not yet audited