## Sheet1
Page (HubSpot Editor) | Live URL | Page Type | Priority | AISEO | Meta Desc | Images Alt Text | Brand Update (Images) | Content Update (New Brand) | Schema / FAQ | Internal Linking | Owner / Assigned To | Target Date | Date Completed | % Complete | Notes / Team Comments | Recommended Page Title | Recommended Meta Description | Image Changed? - Review Alt | Billed - SEO | Billed - Schema | STILL TO BILL | Bill Date | SEO Research | AISEO / SEO | Schema Development | SEO Content Creation | SEO Content Addition | Web Pages Copy | Web Updates | SEO Tracking / HubSpot | Web Graphics Refresh
Aerospace packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/aerospace-packaging/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-24 | 57.14% | Implemented live 2026-06-24 (title, meta, alt - C-P Flexible Packaging brand). Service JSON-LD (gcpflexpack.com) ready to paste in Head HTML; confirm prod path. Footer cert names TBD. | Aerospace Packaging ¦ ESD, Flame-Retardant & Cleanroom Films | Protect aerospace parts with custom flexible packaging—ESD, flame-retardant & cleanroom films built for aviation. Talk to C-P Flexible Packaging today. | Yes | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Autoclave bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags/autoclave-bags | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-24 | 57.14% | Implemented live 2026-06-24 (title, meta, alt - C-P brand). Service JSON-LD ready to paste in Head HTML. Footer cert names TBD. | Autoclave Bags ¦ Steam-Sterilizable Polypropylene Bags | Custom autoclave bags in polypropylene for steam & ETO sterilization of medical instruments and biohazard waste. Get a quote from C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-24 | 57.14% | Implemented live 2026-06-24 (title, meta, alt - C-P brand). CollectionPage JSON-LD ready. Add internal links to bag sub-pages. Footer cert names TBD. | Functional Bags & Pouches ¦ Cleanroom, Static-Shielding & Poly Bags | Custom bags & pouches—autoclave, cleanroom, EMI static-shielding, nylon & poly for medical, electronics & aerospace. Contact C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Bags with customized die-cut windows ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/laser-die-cut-window-rollstock | Product |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-06-24 | 42.86% | Implemented live 2026-06-24 (title, meta, alt - C-P brand). Page is die-cut windows (not scored). No schema for this page. Footer cert lead BRCGS/SQF/AIB - confirm. | Laser Die-Cut Window Rollstock ¦ Product Visibility Packaging | Patented laser die-cut window rollstock adds product visibility & shelf life for snacks, bakery & meats. Discover DCRS from C-P Flexible Packaging. |  | Billed | N/A | - |  | X | X |  |  |  |  | X | X
Child-Resistant Flexible Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/child-resistant-flexible-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-06-24 | 42.86% | Implemented live 2026-06-24 (title, meta, alt - C-P brand). Emphasize ASTM D3475 in copy. No schema for this page. Footer cert lead BRCGS/SQF/AIB - confirm. | Child-Resistant Flexible Packaging ¦ ASTM D3475 Pouches & Film | ASTM D3475-compliant child-resistant flexible packaging for cannabis, medications & chemicals—secure yet senior-friendly. Talk to C-P Flexible Packaging. |  | Billed | N/A | - |  | X | X |  |  |  |  | X | X
Cleanroom bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags/cleanroom-bags | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25 (title, meta, alt - C-P brand). Service JSON-LD ready to paste in Head HTML. Footer cert lead BRCGS/SQF/AIB - confirm. | Cleanroom Bags ¦ FDA-Compliant Medical & Electronics Packaging | Cleanroom bags made in contamination-controlled facilities to protect medical devices & electronics. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Coffee & beverage packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/coffee | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-24 | 57.14% | Implemented live 2026-06-24 (title, meta, alt - C-P brand). Service JSON-LD ready to paste in Head HTML. Footer cert lead BRCGS/SQF/AIB - confirm. | Coffee & Beverage Packaging ¦ Bags, Pods, Sleeves & Labels | Custom coffee & beverage packaging—retail bags, pod overwraps, shrink sleeves & roll-fed labels, with sustainable options. Contact C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Cold-Seal Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/cold-seal-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25 (title, meta, alt - C-P brand). Service JSON-LD ready to paste in Head HTML. Co-packer guide download = conversion asset. | Cold-Seal Packaging ¦ Heat-Sensitive Bar & Snack Wraps | Cold-seal packaging protects heat-sensitive bars and snacks at high line speeds without heat. Get the co-packer guide from C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Compostable Flexible Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/compostable-flexible-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25 (title, meta, alt - C-P brand). Service JSON-LD ready. BPI cert = trust signal. | Compostable Flexible Packaging ¦ BPI-Certified Sustainable Films | BPI-certified compostable flexible packaging—films, pouches, bags & overwraps that break down cleanly. Explore GreenStream by C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Compostable Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/compostable-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25 (title, meta, alt - C-P brand). Service JSON-LD ready. | Compostable Pouches ¦ Plant-Based Stand-Up & Frac Packs | 100% compostable pouches in plant-based films for coffee, snacks & home care—stand-up, box & frac packs. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Confectionery packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/confectionery | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25. Title/meta + 3 image alts (all empty) + Service JSON-LD ready. | Confectionery Packaging ¦ Custom Pouches, Rollstock & Shrink Sleeves | Custom confectionery packaging for candy & sweets—stand-up pouches, rollstock, shrink sleeves & cold-seal. Contact C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Cookie & bakery product packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/cookies-bakery-products/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25. Title/meta + 4 image alts + Service JSON-LD ready. IMG_2405 alt is best-guess - confirm subject. | Cookie & Bakery Packaging ¦ Resealable Pouches, Slug Packs & Flow Wrap | Cookie & bakery packaging with reclose technology—stand-up pouches, slug packs & flow wrap that protect freshness. Talk to C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Custom shrink bands ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/shrink-bands | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 3 image alts + Service JSON-LD ready. Well-structured page. | Shrink Bands ¦ Custom PVC & PETG Tamper-Evident Bands | Custom PVC & PETG shrink bands for tamper-evident sealing, bundling & upselling—printed or clear, high shrink ratios. Contact C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Download Your Cold-Seal Packaging Guide ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/cold-seal-packaging-guide | Resource |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-06-26 | 42.86% | Implemented live 2026-06-26. Title/meta only - lead-gen landing page, no content images, no schema needed. | Cold-Seal Packaging Guide ¦ Free Download for Co-Packers | Download the free cold-seal packaging guide—benefits, short-run feasibility & how to vet a supplier. Get your copy from C-P Flexible Packaging. |  | Billed | N/A | - | 2026-07-03 | X | X |  |  |  |  | X | X
Flat-Bottom Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/flat-bottom-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 1 image alt + Service JSON-LD ready. Keep BOX POUCHES® registered mark. | Flat-Bottom Pouches ¦ Box & Quad-Seal Pouches with Shelf Appeal | Flat-bottom pouches—BOX POUCHES® & quad-seal—for standout shelf presence and stability across coffee, snacks & pet food. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Flexible Package Design & Consultation ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/capabilities/flexible-package-design-and-consultation | Capability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26 (title, meta, alt, schema). Title/meta + 1 image alt + Service JSON-LD ready. Light page - consider more process visuals. | Flexible Package Design & Consultation ¦ Custom Packaging Engineering | Flexible package design & consultation—from concept to prototype with barrier testing and material expertise. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-06 | X | X | X |  |  |  | X | X
Flexible Packaging Prepress Services ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/capabilities/flexible-packaging-prepress-services/ | Capability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26 (title, meta, alt, schema). Title/meta + 1 image alt + Service JSON-LD ready. In-house platemaking = differentiator. | Flexible Packaging Prepress Services ¦ In-House Platemaking | In-house flexible packaging prepress & platemaking for greater control, color consistency & faster lead times. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-06 | X | X | X |  |  |  | X | X
GreenStream Sustainable Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/sustainable-packaging/greenstream-products/ | Sustainability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26 (title, meta, alt, schema - all done). Canonical GreenStream page. Keep GreenStream trademark in copy. | GreenStream Sustainable Packaging ¦ Recyclable, PCR & Compostable | GreenStream sustainable packaging—recyclable, PCR, compostable, bio-sourced & paper structures with How2Recycle support. Talk to C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Health & wellness packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/health-wellness-packaging/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26 (title, meta, alt, schema). Add a visible caption + source citation under the consumer-demand chart for E-E-A-T. | Health & Wellness Packaging ¦ Supplements, Personal Care & More | Flexible packaging for health & wellness products—vitamins, supplements, personal care & better-for-you foods. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
HFFS and VFFS rollstock ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/hffs-vffs-rollstock | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26 (title, meta, alt, schema). Title/meta + 1 image alt + Service JSON-LD ready. | HFFS & VFFS Rollstock ¦ Form/Fill/Seal Packaging Films | HFFS & VFFS rollstock engineered for machinability and consistent seals on your form/fill/seal lines. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
High Burst Strength Packaging ¦ Over the Mountain Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/high-burst-strength-flexible-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 1 image alt + Service JSON-LD ready. OTM seal strength differentiator. | High Burst Strength Packaging ¦ OTM Laminations for Snacks | High burst strength flexible packaging (OTM) with superior seal strength to survive altitude and shipping—ideal for snacks. Talk to C-P Flexible Packaging. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
High-Barrier Flexible Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/high-barrier-flexible-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 1 image alt + Service JSON-LD ready. Clear high-barrier = foil alternative. | High-Barrier Flexible Packaging ¦ Oxygen & Moisture Barrier Films | High-barrier flexible packaging films that block oxygen and moisture to extend shelf life—clear or foil-free options. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
High-Definition Flexographic Printing ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/capabilities/high-definition-flexographic-printing/ | Capability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 1 image alt + Service JSON-LD ready. H1 is generic Capabilities - change to HD Flexographic Printing. | HD Flexographic Printing ¦ Extended Gamut Packaging Printing | HD flexographic printing with extended gamut for vivid, consistent color at lower cost across multiple SKUs. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Inno-Lok® Pre-Zippered Rollstock ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/inno-lok-pre-zippered-rollstock | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-26 | 57.14% | Implemented live 2026-06-26. Title/meta + 2 image alts + Service JSON-LD ready. Keep Inno-Lok® registered mark. | Inno-Lok® Pre-Zippered Rollstock ¦ Resealable VFFS Packaging | Inno-Lok® pre-zippered rollstock adds a resealable zipper on your existing VFFS line—no equipment changes. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Internal Recycling Center ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/sustainable-packaging/internal-recycling-facility/ | Sustainability |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-06-26 | 42.86% | Implemented live 2026-06-26. Title/meta + 1 image alt. Informational sustainability page - no schema applies. Feature recycling stats. | Internal Recycling Facility ¦ PE Scrap Recycling & Waste Diversion | Inside C-P's internal recycling facility—diverting millions of pounds of PE scrap from landfill each year. Explore our sustainability commitment. |  | Billed | Billed | - |  | X | X | X |  |  |  | X | X
Laser-Scored Pouches Easy-Open Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/laser-scored-pouches-easy-open-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-25 | 57.14% | Implemented live 2026-06-25 (title, meta, alt - C-P brand). Distinct from die-cut window page. Service JSON-LD ready to paste in Head HTML. | Laser-Scored Pouches ¦ Easy-Open Flexible Packaging | Laser-scored pouches deliver easy-open, tear-anywhere convenience without sacrificing barrier or seal strength. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-06 | X | X | X |  |  |  | X | X
Lidding films ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/lidding-films | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-28 | 57.14% | Implemented live 2026-06-28. Title/meta + 5 image alts + Service JSON-LD ready. Keep Affirm™ trademark. | Lidding Films ¦ Peelable & High-Barrier Films for Rigid Containers | Affirm™ lidding films—peelable, lockdown & peel-reseal—for produce, meats, dairy & prepared meals. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Markets - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-28 | 57.14% | Implemented live 2026-06-28. Title/meta + 8 image alts + CollectionPage JSON-LD ready. Hub - reuse alts on market pages. | Markets ¦ Flexible Packaging for Snacks, Coffee, Pet Food & More | Flexible packaging expertise across snacks, bakery, coffee, pet food, confectionery, health, medical & aerospace markets. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Matte and gloss pouches - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/matte-and-gloss-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-28 | 57.14% | Implemented live 2026-06-28. Title/meta + 1 image alt + Service JSON-LD ready. Premade pouch format - distinct from rollstock matte/gloss; cross-link. | Matte & Gloss Pouches ¦ High-Impact Stand-Up Pouch Finishes | Matte & gloss stand-up pouches with registered finish effects for massive shelf impact and brand standout. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Matte/Gloss Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/matte-gloss-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-28 | 57.14% | Implemented live 2026-06-28. Title/meta + 1 image alt + Service JSON-LD ready. Rollstock format - distinct from matte/gloss pouches; cross-link. | Matte/Gloss Flexible Packaging ¦ Registered Finish Effects | Matte/gloss flexible packaging with registered finish effects that add 3D shelf impact and brand recognition. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Medical & electronics cleanroom packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/medical-electronics-cleanroom-packaging/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-29 | 57.14% | Implemented live 2026-06-29. Title/meta + 8 image alts (all empty) + Service JSON-LD ready. Lead with largest cleanroom manufacturer. | Medical & Electronics Cleanroom Packaging ¦ ISO-Class Films | Cleanroom packaging for medical devices and electronics—antistatic, ISO-class films built for contamination control. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Nylon bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags/nylon-bag | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-29 | 57.14% | Implemented live 2026-06-29. Title/meta + 1 image alt + Service JSON-LD ready. Link to Cleanroom Bags + Bags hub. | Nylon Bags ¦ Tough, Abrasion-Resistant Cleanroom & Lab Packaging | Tough, abrasion-resistant nylon bags with high-barrier protection for cleanroom, medical, lab and chemical use. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Our companies - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/about-us/our-companies | Page |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-06-29 | 42.86% | Implemented live 2026-06-29. Title/meta + 5 image alts (company names). About page - no schema applies. | Our Companies ¦ The C-P Flexible Packaging Family of Brands | Meet the C-P Flexible Packaging family—Cleanroom Film & Bags, Fruth, Preferred Packaging, Bass Flexible Packaging and Intelligraphix. |  | Billed | N/A | - | 2026-07-03 | X | X |  |  |  |  | X | X
Our Flexible Packaging Technology ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/flexible-packaging-technology | Page |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-29 | 57.14% | Implemented live 2026-06-29. Title/meta + 7 image alts + Service JSON-LD ready. H1 is generic Technology - change to Flexible Packaging Technology. | Flexible Packaging Technology ¦ Reclose, HD Print, Laser & More | Explore C-P's flexible packaging technology—reclose, extended-gamut HD print, die-cut windows, Inno-Lok®, laser scoring & HPP lidstock. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Our Flexible Packaging Products ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-06-29 | 57.14% | Implemented live 2026-06-29. Title/meta + 7 image alts + CollectionPage JSON-LD ready. H1 is generic Products - change to Flexible Packaging Products. Hub - reuse alts. | Flexible Packaging Products ¦ Pouches, Rollstock, Labels & Bags | Explore the full range of flexible packaging products—premade pouches, printed rollstock, labels, sleeves, cold-seal & bags. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-03 | X | X | X |  |  |  | X | X
Package Finishing and Pouch Converting ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/capabilities/finishing-slitting-flexible-packaging/ | Capability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-08 | 57.14% | Audited 2026-06-26. Title/meta + 1 image alt + Service JSON-LD ready. H1 is generic Capabilities - change to Package Finishing & Pouch Converting. | Package Finishing & Pouch Converting ¦ Slitting & Reseal Integration | In-house finishing, slitting and pouch converting—plus reseal and sleeve integration—for finished flexible packaging. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-08 | X | X | X |  |  |  | X | X
Paper flexible packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/paper-flexible-packaging/ | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-08 | 57.14% | Audited 2026-06-26. Title/meta + 3 image alts + Service JSON-LD ready. Keep GreenStream trademark. Distinct from Paper Pouches - cross-link. | Paper Flexible Packaging ¦ Recyclable & Compostable GreenStream™ Paper | Paper-based flexible packaging with an eco-conscious feel—recyclable and compostable GreenStream™ Paper structures. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-08 | X | X | X |  |  |  | X | X
Paper pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/paper-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-09 | 57.14% | Audited 2026-06-26. Title/meta + 4 image alts + Service JSON-LD ready. Distinct from Paper Flexible Packaging (rollstock) - cross-link. | Paper Pouches ¦ Recyclable & Compostable GreenStream™ Paper Pouches | Recyclable and compostable paper pouches in GreenStream™ Paper—PFAS-free, barrier options for a circular economy. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-09 | X | X | X |  |  |  | X | X
Peel and Reseal Rollstock / Cookie Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/peel-reseal-rollstock | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-09 | 57.14% | Audited 2026-06-26. Title/meta + 3 image alts + Service JSON-LD ready. Cross-link to Cookie & Bakery (shared reclose theme). | Peel & Reseal Rollstock ¦ Award-Winning Reclose Technology | Peel & reseal rollstock with seamless, bottom-applied reclose technology consumers love—ideal for cookies & snacks. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-09 | X | X | X |  |  |  | X | X
Pet food packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/pet-foods/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-10 | 57.14% | Audited 2026-06-26. Title/meta + 2 image alts + Service JSON-LD ready. Strong internal-link hub. | Pet Food Packaging ¦ Stand-Up Pouches for Food & Treats | Custom pet food packaging—stand-up pouches, resealable bags & rollstock for pet food and treats, with sustainable options. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-10 | X | X | X |  |  |  | X | X
Poly bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags/poly-bags | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-13 | 57.14% | Audited 2026-07-10. Title/meta + 8 image alts + Service JSON-LD ready. Strong keyword-rich page. | Poly Bags ¦ Custom-Printed Polyethylene Bags & Roll Stock | High-performance poly bags in every format—wicketed, gusseted, flip-top, die-cut handle & roll stock—custom printed. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-13 | X | X | X |  |  |  | X | X
Pouches With Handles ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/pouches-with-handles | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-13 | 57.14% | Audited 2026-07-10. Title/meta + 1 image alt + Service JSON-LD ready. Link to related pouch formats. | Pouches With Handles ¦ Easy-Carry Stand-Up Pouch Packaging | Pouches with handles for easy carrying, pouring and dispensing—die-cut and ergonomic handles for beverages, pet food & more. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-13 | X | X | X |  |  |  | X | X
Privacy Policies - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/privacy-policy | Page |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-07-24 | 42.86% | Audited 2026-07-15. Title/meta only - legal/compliance page, no images, no schema. | Privacy Policy ¦ C-P Flexible Packaging | C-P Flexible Packaging privacy policy, including California employee/applicant notice and our cookies policy. |  | Billed | N/A | - | 2026-07-24 | X | X |  |  |  |  | X | X
Recyclable Flexible Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/recyclable-flexible-packaging | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-24 | 57.14% | Audited 2026-07-15. Title/meta + 1 image alt + Service JSON-LD ready. Distinct from Recyclable Pouches - cross-link. | Recyclable Flexible Packaging ¦ Mono-Material & PCR Films | Recyclable flexible packaging in mono-material PE and up to 100% post-consumer recycled (PCR) films. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-24 | X | X | X |  |  |  | X | X
Recyclable Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/recyclable-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-24 | 57.14% | Audited 2026-07-15. Title/meta + 1 image alt + Service JSON-LD ready. Distinct from Recyclable Flexible Packaging (rollstock) - cross-link. 60% less plastic proof point. | Recyclable Pouches ¦ Mono-Material & PCR Stand-Up Pouches | Recyclable pouches in mono-material PE and PCR resins—up to 60% less plastic than rigid containers. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-24 | X | X | X |  |  |  | X | X
Request a Consultation ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/request-a-consultation | Page |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-07-24 | 42.86% | Audited 2026-07-15. Title/meta only - lead-gen landing page, no schema. H1 is sitewide CTA heading - change to Request a Consultation. | Request a Consultation ¦ Flexible Packaging Experts | Struggling with delivery, quality or cost from your packaging supplier? Schedule a consultation with C-P Flexible Packaging. |  | Billed | N/A | - | 2026-07-24 | X | X |  |  |  |  | X | X
Roll-fed Labels ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/roll-fed-labels | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-24 | 57.14% | Audited 2026-07-15. Title/meta + 2 image alts + Service JSON-LD ready. Extended gamut + no-adhesive are differentiators. | Roll-Fed Labels ¦ 360° Wraparound Film Labels for Bottles & Jars | Roll-fed wraparound labels deliver bold 360° branding without adhesive, with extended gamut printing. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-24 | X | X | X |  |  |  | X | X
Shrink Sleeves ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/shrink-sleeves | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-24 | 57.14% | Audited 2026-07-24. Title/meta + 5 image alts + Service JSON-LD ready. Distortion-tested graphics = differentiator. | Shrink Sleeves ¦ 360° Shrink Sleeve Labels & Sustainable Options | Full-body shrink sleeves with distortion-tested graphics for maximum shelf impact—plus recyclable options. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-24 | X | X | X |  |  |  | X | X
Slider Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/slider-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-24 | 57.14% | Audited 2026-07-24. Title/meta + 1 image alt + Service JSON-LD ready. Slider variety = differentiator. | Slider Pouches ¦ Resealable Slider Zipper Pouch Packaging | Slider pouches with easy-open, resealable zippers—low-profile, high-retention and child-resistant options. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-24 | X | X | X |  |  |  | X | X
Snack food packaging - C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/markets/snack-products/ | Market |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-27 | 57.14% | Audited 2026-07-24. Title/meta + 3 image alts + Service JSON-LD ready. Link to snack formats. | Snack Food Packaging ¦ Pillow Bags, Flow Wrap & Stand-Up Pouches | Custom snack food packaging—pillow bags, flow wrap, stand-up pouches & rollstock with easy-open and resealable options. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-27 | X | X | X |  |  |  | X | X
Solar-powered Manufacturing ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/sustainable-packaging/solar-powered-manufacturing | Sustainability |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  | 2026-07-27 | 42.86% | Audited 2026-07-24. Title/meta + 2 image alts. Informational sustainability page - no schema. Feature solar/CO2 figures. | Solar-Powered Manufacturing ¦ Renewable Energy at C-P | C-P Flexible Packaging powers its cleanroom facility with on-site solar, cutting carbon emissions and energy costs. Explore our sustainability commitment. |  | Billed | N/A | - | 2026-07-27 | X | X |  |  |  |  | X | X
Spouted Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/spouted-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-27 | 57.14% | Audited 2026-07-24. Title/meta + 1 image alt + Service JSON-LD ready. Rigid-to-flexible migration angle. | Spouted Pouches ¦ Stand-Up Pouches With Spout Fitments | Spouted pouches deliver easy pouring and portability—a lightweight alternative to rigid bottles for beverages & more. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-27 | X | X | X |  |  |  | X | X
Stand-up Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/stand-up-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-27 | 57.14% | Audited 2026-07-27. Title/meta + 1 image alt + Service JSON-LD ready. Pouch-format hub - link to all pouch types. | Stand-Up Pouches ¦ Custom Premade Pouches With Any Closure | Custom stand-up pouches with any closure—zipper, slider, spout or resealable—plus recyclable & compostable options. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-27 | X | X | X |  |  |  | X | X
Static shielding bags ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/bags/emi-static-shielding-bags | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-27 | 57.14% | Audited 2026-07-27. Title/meta + 2 image alts + Service JSON-LD ready. ISO 9001 + Faraday-cage trust signals. | EMI Static Shielding Bags ¦ ESD Protection for Electronics | EMI static shielding bags with multilayer Faraday-cage construction to protect electronics from static and ESD. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-27 | X | X | X |  |  |  | X | X
Stick Packs ¦ Stick Pack Film Laminations ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/stick-pack-film-laminations | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-27 | 57.14% | Audited 2026-07-27. Title/meta + 1 image alt + Service JSON-LD ready. Single-serve/VFFS angle. | Stick Packs ¦ Single-Serve Stick Pack Film Laminations | Stick pack film laminations for single-serve, on-the-go portability—engineered for high-speed VFFS lines. Talk to C-P Flexible Packaging today. |  | Billed | Billed | - | 2026-07-27 | X | X | X |  |  |  | X | X
Stretch Sleeves ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/stretch-sleeves | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-28 | 57.14% | Audited 2026-07-27. Title/meta + 5 image alts + Service JSON-LD ready. Mono-material + C-FiT. Cross-link Shrink Sleeves. | Stretch Sleeves ¦ Recyclable 360° Mono-Material Labels | Recyclable stretch sleeves in mono-material PE for 360° branding on bottles and jugs—no adhesive, no distortion. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-28 | X | X | X |  |  |  | X | X
Sustainable Packaging ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/sustainable-packaging/ | Sustainability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-28 | 57.14% | Audited 2026-07-27. Title/meta + 4 image alts + CollectionPage JSON-LD ready. Top sustainability hub. Keep GreenStream trademark. | Sustainable Packaging ¦ Recyclable, Compostable & PCR Solutions | Sustainable flexible packaging—recyclable, compostable, PCR and renewable materials, plus source reduction and GreenStream™. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-28 | X | X | X |  |  |  | X | X
Thermoformed Food Trays ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/thermoformed-food-trays/ | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-28 | 57.14% | Audited 2026-07-27. Title/meta + 4 image alts + Service JSON-LD ready. Dual-market. Preferred Packaging heritage. | Thermoformed Food Trays ¦ Retail & Institutional Meal Trays | Thermoformed food trays for retail produce and meat plus institutional meal service—custom-converted and microwavable. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-28 | X | X | X |  |  |  | X | X
Zipper Pouches ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/zipper-pouches | Product |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  | 2026-07-28 | 57.14% | Audited 2026-07-27. Title/meta + 1 image alt + Service JSON-LD ready. Cost-effective resealable hook. Powder-Zip mark. | Zipper Pouches ¦ Cost-Effective Resealable Premade Pouches | Zipper pouches with press-to-close, double-lock and child-resistant closures—the most cost-effective resealable pouch. Talk to C-P Flexible Packaging. |  | Billed | Billed | - | 2026-07-28 | X | X | X |  |  |  | X | X
C-P Lakeville, MN Location ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/lakeville-minnesota/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-28. NEW page (location). Title/meta + 1 image alt + LocalBusiness JSON-LD ready. H1 weak (C-P Lakeville). Keep NAP consistent w/ Google Business Profile. | Lakeville, MN Flexible Packaging Plant ¦ C-P Flexible Packaging | Visit C-P Flexible Packaging's Lakeville, MN plant-custom flexible packaging, lidding, rollstock & pouches. 8235 220th St W. Call (800) 328-4556. |  | Billed | Billed | - | 2026-08-13 | X | X | X |  |  |  | X | X
C-P York, PA Location ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/c-p-york/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-28. NEW page (location). Title/meta + 1 image alt + LocalBusiness JSON-LD ready. H1 weak (C-P York). Image 1headquarters.webp has NO alt text-creative to add. Keep NAP consistent w/ Google Business Profile. | York, PA Flexible Packaging Plant ¦ C-P Flexible Packaging | C-P Flexible Packaging's York, PA facilities-240,000 sq ft of SQF-certified space for HD flexo printing, pouches & lamination. Call (800) 815-0667. |  | Billed | Billed | - | 2026-07-30 | X | X | X |  |  |  | X | X
Preferred Packaging (Norcross, GA) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/preferred-packaging/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-28. NEW page (location, sub-brand). Title/meta + 1 image alt + LocalBusiness JSON-LD ready. H1 generic (Preferred Packaging)-tie to parent. Keep NAP consistent w/ Google Business Profile. | Preferred Packaging - Norcross, GA ¦ C-P Flexible Packaging | Preferred Packaging, a C-P Flexible Packaging company in Norcross, GA-custom flexible packaging serving the Atlanta metro. Call (770) 416-0088. |  | Billed | Billed | - | 2026-07-30 | X | X | X |  |  |  | X | X
C-P Buffalo, NY Location ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/c-p-buffalo/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-30. NEW page (location). Title/meta + 1 image alt + LocalBusiness JSON-LD ready. H1 weak (C-P Buffalo). Alt filename-style. Keep NAP consistent w/ Google Business Profile. | Buffalo, NY Flexible Packaging Plant ¦ C-P Flexible Packaging | C-P Flexible Packaging's Buffalo, NY plant-AIB-certified 10-color HD flexo printing, lamination, pouches & cold-seal. Call (716) 825-7710. |  | Billed | Billed | - | 2026-08-13 | X | X | X |  |  |  | X | X
C-P Aurora, ON Location (Canada) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/aurora-ontario-canada/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-30. NEW page (location, CANADA). LocalBusiness JSON-LD w/ addressCountry=CA. H1 weak (C-P Aurora). Only Canadian plant-own Google Business Profile (CA). | Aurora, ON Flexible Packaging Plant ¦ C-P Flexible Packaging | C-P Flexible Packaging's Aurora, Ontario plant-custom printed flexible packaging, rollstock & pouches for Canadian brands. Call (800) 565-3407. |  | Billed | Billed | - | 2026-08-13 | X | X | X |  |  |  | X | X
C-P Bristol, PA Location ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/c-p-bristol/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-30. NEW page (location). LocalBusiness JSON-LD ready. H1 weak (C-P Bristol). Image c-p-bristol.webp has NO alt text-creative to add. Keep NAP consistent. | Bristol, PA Flexible Packaging Plant ¦ C-P Flexible Packaging | C-P Flexible Packaging's Bristol, PA plant-125,000 sq ft of SQF-certified platemaking, printing, converting & finishing. Call (215) 860-7676. |  | Billed | Billed | - | 2026-08-13 | X | X | X |  |  |  | X | X
C-P Fond du Lac, WI Location ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/fond-du-lac-wisconsin/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-30. NEW page (location). LocalBusiness JSON-LD ready. H1 weak (C-P Fond du Lac). Alt filename-style. Keep NAP consistent w/ Google Business Profile. | Fond du Lac, WI Flexible Packaging Plant ¦ C-P Flexible Packaging | C-P Flexible Packaging's Fond du Lac, WI plant-10-color flexo printing, laminating, custom slitting & prepress. Call (920) 922-8212. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Fruth Custom Packaging (Placentia, CA) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/locations/placentia-california/ | Location |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-07-30. NEW page (location, sub-brand Fruth). LocalBusiness JSON-LD w/ parentOrganization. H1 generic. Image fruth-building.webp NO alt text-creative to add. | Fruth Custom Packaging - Placentia, CA ¦ C-P Flexible Packaging | Fruth Custom Packaging, a C-P Flexible Packaging company in Placentia, CA-blown film, flexo printing & specialty bags. Call (714) 993-9955. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Extrusion & Adhesive Lamination ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/capabilities/extrusion-adhesive-lamination/ | Capability |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (capability). Title/meta + Service JSON-LD ready. Completes capabilities set 5/5. H1 already strong-no change. Image technology-coex-lamination.webp has NO alt text-creative to add. | Extrusion & Adhesive Lamination ¦ C-P Flexible Packaging | C-P Flexible Packaging engineers multilayer films with extrusion & adhesive lamination-custom barrier, puncture resistance & downgauging. Learn more. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Premade Pouches (Category Index) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/premade-pouches/ | Category |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (category index). CollectionPage JSON-LD (ItemList of 11 pouch pages). CRITICAL: on-page H1 wrongly reads 'Printed rollstock'-must change to 'Premade Pouches'. No content images. | Premade Pouches ¦ Stand-Up, Zipper & Spouted ¦ C-P Flexible Packaging | Explore C-P Flexible Packaging's premade pouches-stand-up, zipper, slider, spouted, flat-bottom & more, in recyclable & compostable options. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Printed Rollstock (Category Index) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/products/printed-rollstock/ | Category |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (category index). CollectionPage JSON-LD (ItemList of 14 rollstock pages). H1 'Printed rollstock' correct but lowercase-title-case it. No content images. | Printed Rollstock ¦ Lidding, Barrier & More ¦ C-P Flexible Packaging | Explore C-P Flexible Packaging's printed rollstock films-high-barrier, lidding, peel-reseal, shrink bands & recyclable options for form-fill-seal lines. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Home (Homepage) ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/ | Home |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (homepage). Title/meta + ORGANIZATION JSON-LD (name, logo, founding 1958, HQ, phone, LinkedIn)-most important schema on site. 10 content images need alt (verify current). H1 tagline OK. Update logo URL in schema before publish. | Custom Flexible Packaging & Printing ¦ C-P Flexible Packaging | C-P Flexible Packaging delivers custom printed rollstock, pouches, labels & sustainable packaging-60 years of HD flexo expertise. Explore our range. |  | Billed | Billed | - | 2026-08-17 | X | X | X |  |  |  | X | X
About Us ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/about-us | Corporate |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (about/E-E-A-T). Title/meta + AboutPage JSON-LD (org, founding 1958). H1 strong-no change. Image about-image.webp alt filename-style-replace. | About C-P Flexible Packaging ¦ 60+ Years of Expertise | Since 1958, C-P Flexible Packaging has grown into a top-25 U.S. converter-800,000+ sq ft of SQF-certified space across nine facilities. Our story. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Contact Us ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/contact/ | Contact |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (contact). Title/meta + ContactPage JSON-LD. H1 'Contact us' generic-change to 'Contact C-P Flexible Packaging'. NAP: abbreviations standardized 8/14 (York/Buffalo/Fond du Lac/Fruth/Aurora spelled out to match schema)-now consistent w/ location pages. STILL TO DO: verify all 9 vs Google Business Profiles (GBP is master). | Contact C-P Flexible Packaging ¦ 9 Plant Locations | Contact C-P Flexible Packaging-9 manufacturing locations across the US & Canada. Call (800) 815-0667 or message our packaging experts online. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Premade Pouches Glossary ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/glossary/pouch/ | Glossary |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (glossary). Title/meta + DefinedTermSet JSON-LD (~40 terms). H1 lowercase-title-case it. No content images. Cross-link entries to product pages. | Premade Pouches Glossary ¦ C-P Flexible Packaging | A-Z glossary of premade pouch terms from C-P Flexible Packaging-pouch types, seals, zippers, laser scoring & testing. Learn the terminology. |  | Billed | Billed | - | 2026-08-14 | X | X | X |  |  |  | X | X
Flexible Packaging Films Glossary ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/glossary/film/ | Glossary |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (glossary). Title/meta + DefinedTermSet JSON-LD. Current title had no brand + lowercase-use branded/title-cased. H1 lowercase-title-case. No content images. | Flexible Packaging Films Glossary ¦ C-P Flexible Packaging | A-Z glossary of flexible packaging film terms from C-P Flexible Packaging-film types, lamination, HFFS/VFFS, gauge & seal bond. Learn the terms. |  | Billed | Billed | - | 2026-08-15 | X | X | X |  |  |  | X | X
Flexible Packaging Calculator ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/flexible-packaging-calculator/ | Tool |  | Complete | Complete | Complete | Not Started | Not Started | Complete | Not Started |  |  |  | 57.14% | Audited 2026-08-14. NEW page (tool). Title/meta + WebApplication JSON-LD (free BusinessApplication). H1 lowercase-title-case. Strong linkable asset-promote from product pages. | Flexible Packaging Calculator ¦ C-P Flexible Packaging | Free flexible packaging calculator from C-P Flexible Packaging-convert MSI, basis weight, yield, microns to mils & more. Try the tool. |  | Billed | Billed | - | 2026-08-15 | X | X | X |  |  |  | X | X
Careers ¦ C-P Flexible Packaging | https://gcpflexpack-24024882.hs-sites.com/careers | Careers |  | Complete | Complete | Complete | Not Started | Not Started | N/A | Not Started |  |  |  | 42.86% | Audited 2026-08-14. Careers page. Title/meta + all image alts (3 content + 9 facility Flexi Cards) implemented & billed 8/14. NO page schema (add JobPosting per role only). Facility cards had filename-style alts (c-p-york-300x172 etc.)-recommended alts captured in audit doc. | Careers at C-P Flexible Packaging ¦ Join Our Team | Build your career at C-P Flexible Packaging-9 U.S. & Canada locations, medical/dental/401(k) match & a family-first culture. View openings. |  | Billed | N/A | - | 2026-08-14 | X | X |  |  |  |  | X | X
News: CFB Grand Opening - Solar-Powered Cleanroom Facility | https://gcpflexpack-24024882.hs-sites.com/news/cleanroom-film-bags-announces-grand-opening-of-new-solar-powered-cleanroom-packaging-facility | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED 2026-08-17 - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
News: Acquisition of Genpak Flexible | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-announces-acquisition-of-genpak-flexible | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-26 (news acquisition, ~520w). BlogPosting schema. Title was ~87ch-replace. 1 image. Links to Our Companies + sustainability. | C-P Acquires Genpak Flexible ¦ C-P Flexible Packaging | C-P Flexible Packaging acquires Genpak Flexible from The Jim Pattison Group-expanding to 6 North American sites & sustainable packaging. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: IntelliGraphix Systems | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-announces-intelligraphix-systems | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-26 (news division launch, ~450w). BlogPosting schema. Title was ~80ch-replace. 2 images (.jpg->WebP). Links to prepress + HD flexo. | C-P Launches IntelliGraphix Systems (Prepress) ¦ C-P Flexible | C-P Flexible Packaging launches IntelliGraphix Systems-a prepress, platemaking & color-management division for flexographic printers. |  | Billed | Billed | - | 2026-08-27 | X | X | X |  |  |  | X | X
News: Top BRCGS AA Rating for Food Packaging | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-earns-top-brcgs-rating-aa-for-food-packaging-quality-and-safety | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, 2025 BRCGS). BlogPosting schema. Current title good; YEAR in title/H1 distinguishes from 2024 post (row 113). Cross-link the two to fix cannibalization. 1 image. | C-P Earns Top BRCGS AA+ Rating 2025 ¦ C-P Flexible | C-P Flexible Packaging earns the top BRCGS rating (AA+) in a 2025 unannounced audit-affirming its food-safety and packaging quality. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: Lidding Films at IDDBA 2023 | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-showcases-proprietary-lidding-films-for-high-pressure-pasteurization-at-iddba-2023 | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news EVENT, ~280w). BlogPosting schema. Title was ~130ch-replace. 3 images (alt OK, minor). Dated event-light value. Links to lidding + greenstream. | HPP Lidding Films at IDDBA 2023 ¦ C-P Flexible Packaging | C-P Flexible Packaging showcased proprietary high-pressure pasteurization (HPP) lidding films at IDDBA 2023 for fresh, minimally-processed foods. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: Virtual Press-Check Capabilities | https://gcpflexpack-24024882.hs-sites.com/news/introducing-virtual-press-check-capabilities-for-customers-in-critical-infrastructure-industries | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, COVID-era 2020, ~250w). BlogPosting schema. Title was ~119ch-replace. 1 image (.jpg->WebP). Dated-light value. Links to HD flexo + prepress. | Virtual Press Check Capabilities ¦ C-P Flexible Packaging | C-P Flexible Packaging launches virtual press-check capabilities-approve packaging graphics remotely via video, built for critical-infrastructure customers. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: Acquires Preferred Packaging (GA) | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-acquires-preferred-packaging-in-georgia | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news acquisition, ~420w). BlogPosting schema. Title was ~87ch-replace. No images. Links to Preferred location + Our Companies + thermoformed. | C-P Acquires Preferred Packaging (Georgia) ¦ C-P Flexible | C-P Flexible Packaging acquires Preferred Packaging in Georgia-expanding refrigerated & frozen meal packaging with thermoformed solutions. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: 2024 MD&M Show | https://gcpflexpack-24024882.hs-sites.com/news/2024-mdm-show-c-p-flexible-packaging/ | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED 2026-08-17 - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
News: New Poly-Bag Manufacturing Investment | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-invests-in-new-poly-bag-manufacturing-capabilities | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, ~350w). BlogPosting schema. Title was ~97ch-replace. 3 images (1 needs alt). Links to poly-bags + Buffalo location. | New Poly Bag Manufacturing at C-P Buffalo ¦ C-P Flexible | C-P Flexible Packaging expands poly bag manufacturing in Buffalo with 3 new Hudson-Sharp lines for food, healthcare & industrial demand. |  | Billed | Billed | - | 2026-08-24 | X | X | X |  |  |  | X | X
News: Dave Klopp Joins as VP of Sales | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-welcomes-dave-klopp-as-vice-president-of-sales | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED 2026-08-17 - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
Learning Center: Vetting Cold-Seal Suppliers | https://gcpflexpack-24024882.hs-sites.com/learning-center/vetting-potential-cold-seal-packaging-suppliers | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-17 (blog, ~2100 words-strong). BlogPosting schema (pub 2020-05-05). Cold-seal CLUSTER hub-link to cold-seal product + other cluster articles. | How to Choose a Cold-Seal Supplier ¦ C-P Flexible Packaging | How co-packers should vet a cold-seal packaging supplier: 4 criteria-customization, scheduling, quality control & technical support. |  | Billed | Billed | - | 2026-08-17 | X | X | X |  |  |  | X | X
Learning Center: Shrink Bands | https://gcpflexpack-24024882.hs-sites.com/learning-center/shrink-bands | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog, ~850w, pub 2023). BlogPosting schema. Title was 79-char H1 no brand-replace. 4 images (2 need alt). Link to /products/printed-rollstock/shrink-bands. | Why Shrink Bands Deliver Tamper Evidence ¦ C-P Flexible Packaging | 5 reasons shrink bands are the go-to for tamper-evident packaging-affordable, versatile & secure across bottles, jars & more. See why. |  | Billed | Billed | - | 2026-08-19 | X | X | X |  |  |  | X | X
Learning Center: Recyclable Stand-Up Pouches | https://gcpflexpack-24024882.hs-sites.com/learning-center/commercially-viable-recyclable-stand-up-pouches | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-17 (blog, ~1800 words). BlogPosting schema (pub 2020-12-22). Current title TOO LONG (78) + no brand-use recommended. Link to /products/premade-pouches/recyclable-pouches. | Commercializing Recyclable Stand-Up Pouches ¦ C-P Flexible Packaging | How CPG brands commercialize recyclable mono-material PE stand-up pouches-design, equipment fit & FTC compliance. A practical roadmap from C-P. |  | Billed | Billed | - | 2026-08-19 | X | X | X |  |  |  | X | X
Learning Center: What Is Cold-Seal Packaging | https://gcpflexpack-24024882.hs-sites.com/learning-center/what-is-cold-seal-packaging | Learning Center |  | Complete | Complete | Complete |  |  | Complete |  |  |  |  | 57.14% | AUDITED 2026-08-17 (blog). BlogPosting schema (pub 2019-10-16). Title good. Cold-seal CLUSTER-internal-link to /products/cold-seal-packaging + cold-seal guide. | What Is Cold-Seal Packaging? ¦ C-P Flexible Packaging | Cold-seal packaging uses pressure-activated adhesive to seal up to 10x faster than heat-seal-ideal for heat-sensitive bars, chocolate & candy. |  | Billed | Billed | - | 2026-08-17 | X | X | X |  |  |  | X | X
Learning Center (index) | https://gcpflexpack-24024882.hs-sites.com/learning-center | Blog Index |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | Blog listing/index page. Optimize lightly (title/meta) or leave to HubSpot template. | [5 empty] | queued
System: /learning-center/author/admin | https://gcpflexpack-24024882.hs-sites.com/learning-center/author/admin | System (blog) |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | HubSpot blog system page (author). Recommend NOINDEX rather than optimize - inflates page count. | [5 empty] | noindex?
Learning Center: benefits of cold seal packaging | https://gcpflexpack-24024882.hs-sites.com/learning-center/benefits-of-cold-seal-packaging | Learning Center |  | Complete | Complete | Complete |  |  | Complete |  |  |  |  | 57.14% | AUDITED 2026-08-17 (blog). BlogPosting schema (pub 2019-10-16). Cold-seal CLUSTER-link to /products/cold-seal-packaging. | 3 Benefits of Cold-Seal Packaging ¦ C-P Flexible Packaging | 3 advantages of cold-seal packaging: no heat, up to 10x faster speeds, and it runs on your existing heat-seal equipment. See why it fits your line. |  | Billed | Billed | - | 2026-08-17 | X | X | X |  |  |  | X | X
Learning Center: fixing flexible packaging performance print quality issues | https://gcpflexpack-24024882.hs-sites.com/learning-center/fixing-flexible-packaging-performance-print-quality-issues | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog, ~1100w). BlogPosting schema. Title was 86-char H1 no brand-replace. 2 .jpg images (convert to WebP). Links to HD flexo + design capabilities. | Fix Flexible Packaging Performance & Print Issues ¦ C-P Flexible | How to diagnose and fix flexible packaging performance and print-quality issues with your converter-troubleshooting tips from C-P's technical team. |  | Billed | Billed | - | 2026-08-19 | X | X | X |  |  |  | X | X
Learning Center: how an artisan meats company improved their productivity and branding with die cut rollstock | https://gcpflexpack-24024882.hs-sites.com/learning-center/how-an-artisan-meats-company-improved-their-productivity-and-branding-with-die-cut-rollstock | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog CASE STUDY). BlogPosting schema. NEW TITLE/H1: 'How Die-Cut Rollstock Boosted an Artisan Meat Brand''s Productivity' (was 91ch). NEW SLUG: die-cut-rollstock-meat-case-study (was ~90ch)-change NOW pre-launch, no 301. 5 images ALL need alt. Link to laser-die-cut-window-rollstock. | Die-Cut Rollstock Meat Packaging Case Study ¦ C-P Flexible | How an artisan meats company boosted productivity and branding by switching to laser die-cut rollstock for flow-wrapping. A C-P case study. |  | Billed | Billed | - | 2026-08-21 | X | X | X |  |  |  | X | X
Learning Center: how to cut flexible packaging costs eliminate delivery issues | https://gcpflexpack-24024882.hs-sites.com/learning-center/how-to-cut-flexible-packaging-costs-eliminate-delivery-issues | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog, ~1100w). BlogPosting schema. Title was 64-char H1 no brand-add brand. 2 images (alt OK, minor). Links to finishing + about-us. | Cut Flexible Packaging Costs & Delivery Issues ¦ C-P Flexible | How to cut flexible packaging costs and eliminate delivery issues-choose a supplier with the right supply-chain strategy. Tips from C-P. |  | Billed | Billed | - | 2026-08-21 | X | X | X |  |  |  | X | X
Learning Center: redesigning flexible packaging sustainability shelf appeal | https://gcpflexpack-24024882.hs-sites.com/learning-center/redesigning-flexible-packaging-sustainability-shelf-appeal | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog, ~850w). BlogPosting schema. 1 image needs alt. DUP: bare-path copy exists (no /learning-center/)-canonical/301. Links to sustainable-packaging + design. [OPEN: duplicate bare-path URL /redesigning-... is LIVE (200) - find in Website/Landing Pages, delete + 301 to this learning-center URL. Not part of this bill.] | Redesign Flexible Packaging for Sustainability ¦ C-P Flexible | How to redesign flexible packaging for sustainability and stronger shelf appeal-work with your supplier to hit both goals. A guide from C-P. |  | Billed | Billed | - | 2026-08-21 | X | X | X |  |  |  | X | X
Learning Center: short run cold seal packaging for co packers | https://gcpflexpack-24024882.hs-sites.com/learning-center/short-run-cold-seal-packaging-for-co-packers | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-17 (blog, ~1800 words). BlogPosting schema (pub 2020-05-04). Cold-seal CLUSTER-link to /products/cold-seal-packaging. | Short-Run Cold-Seal Packaging for Co-Packers ¦ C-P Flexible | Short-run cold-seal packaging for co-packers-up to 10x faster speeds and lower costs without long runs. See how C-P makes it accessible. |  | Billed | Billed | - | 2026-08-19 | X | X | X |  |  |  | X | X
Learning Center: sustainable wipes packaging 101 | https://gcpflexpack-24024882.hs-sites.com/learning-center/sustainable-wipes-packaging-101 | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (blog, ~1100w). BlogPosting schema. Title fix ' - ' to ' ¦ '. 3 images (alt OK, minor). Links to sustainable-packaging + greenstream. | Sustainable Wipes Packaging 101 ¦ C-P Flexible Packaging | Sustainable wipes packaging 101: recyclable, compostable & PCR options for wipes brands. Explore eco-friendly solutions from C-P Flexible Packaging. |  | Billed | Billed | - | 2026-08-21 | X | X | X |  |  |  | X | X
Learning Center: the benefits of reclose technology | https://gcpflexpack-24024882.hs-sites.com/learning-center/the-benefits-of-reclose-technology | Learning Center |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-17 (blog, ~450 words-lightest). BlogPosting schema (pub 2020-05-06). Title uses ' - ' + lowercase-fix. Link to /products/printed-rollstock/peel-reseal-rollstock. | Peel & Reseal (Reclose) Packaging Benefits ¦ C-P Flexible Packaging | Why reclose (peel & reseal) packaging wins-81% of impulse buyers value resealability. Extend shelf life & keep branding with pressure-sensitive labels. |  | Billed | Billed | - | 2026-08-19 | X | X | X |  |  |  | X | X
Cleanroom Film & Bags (Placentia) - EXCLUDED | https://gcpflexpack-24024882.hs-sites.com/locations/orange-california | Location (Cleanroom) |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | Cleanroom Film & Bags - previously EXCLUDED from C-P scope ('no cleanroom'). Tool audits it; confirm if it should be optimized. | [5 empty] | excluded
News (blog index) | https://gcpflexpack-24024882.hs-sites.com/news | Blog Index |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | Blog listing/index page. Optimize lightly (title/meta) or leave to HubSpot template. | [5 empty] | queued
System: /news/author/admin | https://gcpflexpack-24024882.hs-sites.com/news/author/admin | System (blog) |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | HubSpot blog system page (author). Recommend NOINDEX rather than optimize - inflates page count. | [5 empty] | noindex?
News: cleanroom film bags adds capacity to serve increasing demand for cleanroom nylon films and bags | https://gcpflexpack-24024882.hs-sites.com/news/cleanroom-film-bags-adds-capacity-to-serve-increasing-demand-for-cleanroom-nylon-films-and-bags | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
News: cleanroom film bags expands offering of customized sterilizable packaging | https://gcpflexpack-24024882.hs-sites.com/news/cleanroom-film-bags-expands-offering-of-customized-sterilizable-packaging | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
News: c p expands medical packaging capabilities through fruth division to meet rising demand for biohazard autoclave bags | https://gcpflexpack-24024882.hs-sites.com/news/c-p-expands-medical-packaging-capabilities-through-fruth-division-to-meet-rising-demand-for-biohazard-autoclave-bags | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, pub 2025, ~400w). BlogPosting schema. Current title already good. Links to Autoclave Bags product + Fruth location. | Fruth Expands Autoclave & Biohazard Bag Capacity ¦ C-P | C-P's Fruth division expands U.S.-made autoclave & biohazard bag capacity-medical-grade packaging built for stringent sterilization standards. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: c p flexible packaging acquires fruth custom packaging inc and cleanroom film and bag inc | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-acquires-fruth-custom-packaging-inc-and-cleanroom-film-and-bag-inc | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news acquisition, ~650w). BlogPosting schema. Title was ~116ch-replace. Mentions Cleanroom (legit here). Links to Fruth location + medical market. | C-P Acquires Fruth & Cleanroom Film and Bag ¦ C-P Flexible | C-P Flexible Packaging acquires Fruth Custom Packaging & Cleanroom Film and Bag-expanding West Coast medical, pharma & electronics packaging. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: c p flexible packaging announces acquisition of bass flexible packaging inc | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-announces-acquisition-of-bass-flexible-packaging-inc | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-26 (news acquisition, ~420w). BlogPosting schema. Title was ~101ch-replace. No images. Links to Our Companies + confectionery/health. | C-P Acquires Bass Flexible Packaging ¦ C-P Flexible | C-P Flexible Packaging acquires Bass Flexible Packaging-adding agile, short-lead-time capabilities for confectionery and health & beauty. |  | Billed | Billed | - | 2026-08-27 | X | X | X |  |  |  | X | X
News: c p flexible packaging announces acquisition of prestige pak inc | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-announces-acquisition-of-prestige-pak-inc | News |  | Review | Review | Review |  |  | Review |  |  |  |  | 0% | AUDITED 2026-08-26 (news acquisition, ~425w). BlogPosting schema. Title was ~90ch-replace. 1 image needs alt. Links to Our Companies + snack/confectionery. | C-P Acquires Prestige-Pak (Wisconsin) ¦ C-P Flexible | C-P Flexible Packaging acquires Wisconsin's Prestige-Pak-a 53-year family converter of printed films for snacks, confectionery & baked goods. |  |  |  | pending impl |  | X | X | X |  |  |  |  | X
News: c p flexible packaging announces commitment to convert 50 of companys u s plants to solar power by 2025 | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-announces-commitment-to-convert-50-of-companys-u-s-plants-to-solar-power-by-2025 | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news sustainability, ~310w). BlogPosting schema. Title was ~150ch-replace. No images. Links to Solar-Powered Manufacturing. | C-P Commits to 50% Solar-Powered U.S. Plants by 2025 ¦ C-P | C-P Flexible Packaging commits to converting 50% of its U.S. plants to solar power by 2025-with installations already live in California & Minnesota. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: c p flexible packaging awarded highest achievable brcgs ratings for product quality and safety | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-awarded-highest-achievable-brcgs-ratings-for-product-quality-and-safety | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, 2024 BRCGS). BlogPosting schema. YEAR ADDED to title/H1 to fix cannibalization vs the 2025 BRCGS post (row 82). Cross-link the two. Links to Fond du Lac + Lakeville. Image .jpg->WebP. | C-P Earns Highest BRCGS Ratings 2024 (AA+/AA) ¦ C-P Flexible | C-P Flexible Packaging earns the highest BRCGS ratings-AA+ (Fond du Lac) and AA (Lakeville)-for food-safety and packaging quality. |  | Billed | Billed | - | 2026-08-24 | X | X | X |  |  |  | X | X
News: c p flexible packaging enables rapid development of voortmans resealable cookie packaging | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-enables-rapid-development-of-voortmans-resealable-cookie-packaging | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news CASE, ~250w). BlogPosting schema. Title was ~113ch-replace. Image alt ~180ch-trim. Links to peel-reseal + cookies market. | Voortman Resealable Cookie Packaging Case ¦ C-P Flexible | How C-P Flexible Packaging developed Voortman's resealable cookie packaging in 6 months-easy-open, easy-reseal, no capital investment. |  | Billed | Billed | - | 2026-08-24 | X | X | X |  |  |  | X | X
News: c p flexible packaging launches new website | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-launches-new-website | News |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | QUEUED - blog/news content (HubSpot Blog tool). NOT yet audited. Needs title/meta/Article schema/internal links. | [5 empty] | queued
News: c p flexible packaging teams up with hr pharmaceuticals to donate hand sanitizer in record time | https://gcpflexpack-24024882.hs-sites.com/news/c-p-flexible-packaging-teams-up-with-hr-pharmaceuticals-to-donate-hand-sanitizer-in-record-time | News |  | Review | Review | Review |  |  | Review |  |  |  |  | 0% | AUDITED 2026-08-26 (news, COVID-era 2020, ~1100w-substantial). BlogPosting schema. Current title decent, no brand-add it. 1 image (.jpg->WebP). Links to health market + finishing. | Hand Sanitizer Packaging Supplied in Record Time ¦ C-P Flexible | How C-P Flexible Packaging & HR Pharmaceuticals produced hand-sanitizer packets in record time for frontline workers during COVID-19. |  |  |  | pending impl |  | X | X | X |  |  |  |  | X
News: high performance packaging for extended shelf life refrigerated meals | https://gcpflexpack-24024882.hs-sites.com/news/high-performance-packaging-for-extended-shelf-life-refrigerated-meals | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, ~650w). BlogPosting schema. Title AND H1 extremely long (~155-180ch)-shorten both. No images. Links to lidding + high-barrier. | High-Performance Lidding for Refrigerated Meals ¦ C-P Flexible | C-P's Preferred Packaging + Northwest Frozen launched Affirm lidding film for extended shelf-life refrigerated meals-incl. Oprah's Favorite Things 2022. |  | Billed | Billed | - | 2026-08-26 | X | X | X |  |  |  | X | X
News: introducing c p greenstream portfolio of sustainable packaging solutions | https://gcpflexpack-24024882.hs-sites.com/news/introducing-c-p-greenstream-portfolio-of-sustainable-packaging-solutions | News |  | Complete | Complete | Complete |  |  | Complete | Complete |  |  |  | 71.43% | AUDITED 2026-08-19 (news, ~350w, pub 2020). BlogPosting schema. Title was ~97ch-replace. 2 images need alt. Links to greenstream-products. | C-P GreenStream Sustainable Packaging Portfolio ¦ C-P Flexible | C-P Flexible Packaging launches GreenStream-PCR, compostable & single-source recyclable films accepted at 18,000+ U.S. retail drop-off sites. |  | Billed | Billed | - | 2026-08-24 | X | X | X |  |  |  | X | X
News: preferred packaging a division of c p flexible packaging launches new sustainable greenstream pulp trays | https://gcpflexpack-24024882.hs-sites.com/news/preferred-packaging-a-division-of-c-p-flexible-packaging-launches-new-sustainable-greenstream-pulp-trays | News |  | Review | Review | Review |  |  | Review |  |  |  |  | 0% | AUDITED 2026-08-26 (news, ~550w, 2022 pulp trays). BlogPosting schema. Title was ~130ch-replace. NEAR-DUP of 2025 fiber-trays post-differentiate/cross-link. Links to greenstream + thermoformed. | GreenStream Pulp Trays from Preferred Packaging ¦ C-P Flexible | Preferred Packaging launches GreenStream compostable plant-fiber pulp trays-an eco alternative to plastic for school-meal & food packaging. |  |  |  | pending impl |  | X | X | X |  |  |  |  | X
News: preferred packaging launches greenstream fiber trays a new standard in sustainable meal packaging | https://gcpflexpack-24024882.hs-sites.com/news/preferred-packaging-launches-greenstream-fiber-trays-a-new-standard-in-sustainable-meal-packaging | News |  | Review | Review | Review |  |  | Review |  |  |  |  | 0% | AUDITED 2026-08-26 (news, ~220w, 2025 fiber trays). BlogPosting schema. WRONG IMAGE (poly-bag-dept-low-res.webp)-swap. NEAR-DUP of 2022 pulp-trays post. Light-expand. Links to greenstream. | GreenStream Compostable Fiber Trays ¦ C-P Flexible Packaging | Preferred Packaging launches GreenStream bagasse fiber trays-compostable, curbside-recyclable, PFAS-free & compatible with sustainable lidding. |  |  |  | pending impl |  | X | X | X |  |  |  |  | X
Review: redesigning flexible packaging sustainability shelf appeal | https://gcpflexpack-24024882.hs-sites.com/redesigning-flexible-packaging-sustainability-shelf-appeal | Page (review) |  | Not Started | Not Started | Not Started |  |  | Not Started |  |  |  |  | 0% | Possible DUPLICATE of a /learning-center/ article (bare URL). Verify - may need canonical/redirect. | [5 empty] | review-dup?
Note on S1: CREATIVE TEAM: Set to 'Yes' whenever you change or swap an image on this page. That flags the row (Page + URL turn amber) so the alt text gets re-reviewed. Set back to 'No' once the alt text has been reviewed/updated.
Note on X1: Work-category LABELS only (mark = category touched this page). These are NOT hours - actual hours live in the timesheet. #8 SEO Tracking/HubSpot is client-billable.